## Activities
Module | Page | Section | Sub-section | Item | Element | API | Front end setup | Action | Design
Activities | Dashboard | Grid

## Leads
Module | Page | Section | Sub-section | Item | Field List Ref | Element/Desc | API | Web/Design | Integration | Action | SMS Template required | Email Template Required | Design
Login | Login
| Auto logout | [11 empty] | The seesion shud be lost if 10 mins of in-activity
Leads
All Leads
|  | Grid view | Filters
|  |  |  | Search by name |  | Search on Frist Name, Last Name, Email, Phone | Yes | Yes | Yes
|  |  |  | Last contact |  |  | API changes done | No | No | To Be Removed
|  |  |  | Status |  | To be fetched from DB | Yes | Yes | No
|  |  |  | Delete |  | Delete Selected items | No | Yes | No
|  |  |  | Search button |  |  | Yes | Yes | No
Grid
|  |  |  | checkbox |  | Delete | No | No | No
|  |  |  | Edit |  | Go to Edit button | Yes | Yes | Yes
|  |  |  | Send email |  | Send Email popup | No | No | No
|  |  |  | Send SMS |  | Send SMS popup | No | No | No
|  |  |  | Add note |  | Add Note popup | Yes | Yes | Yes
|  |  |  | add call log |  | Add Call log | Yes | Yes | Partial | Message not submitted error message not coming Error if no message entered
|  |  |  | add email log |  | Add Email log | Yes | Yes | Partial | Without Message not submitted error message not coming Error if no message entered
|  |  |  | add sms log |  | Add SMS log | Yes | Yes | No | Without Message not submitted error message not coming Error if no message entered No Submit working
|  |  |  | set next follow up |  | Add Next Followup | Yes | Yes | Yes | Saving in old Dates
|  |  |  | Qualification |  | View | No | No | No
[6 empty] | Save | Yes | No | No
|  |  |  | Buyer Preferences |  | View | No | Yes | No
[6 empty] | Save | Yes | No | No
|  |  |  | Seller Preferences |  | View | No | Yes | No
[6 empty] | Save | Yes | No | No
|  |  |  | Investor Preferences |  | View | No | Yes | No
[6 empty] | Save | Yes | No | No
|  |  |  | Action - View Details |  | View Basic Lead details | Yes | Yes | Yes
|  |  |  | Edit Leads |  | Field Old values | Yes | Yes | Yes
|  |  |  | Save Lead |  |  | Yes | Yes | Yes
|  |  |  | Action View - All Activities |  | View Old All Activities | Yes | Yes | Yes | Loader is missing
|  |  |  | View Appointments |  | Loading Appointments history | Yes | No | No | Not loading history data
|  |  |  | Save Appointment |  | Saving new appointment in DB | Yes | Yes | Yes
|  |  |  | View Notes |  | Loading Note history | Yes | Yes | Yes
|  |  |  | Save Notes |  | Saving new Note in DB | Yes | No | No | Not Saving Notes, Error
|  |  |  | View Followup |  | Loading history | Yes | Yes | Yes
|  |  |  | Save Followup |  | Saving in DB | Yes | No | No | Not Saving Notes, Error
|  |  |  | Add call log |  | Add Call log | Yes | Yes | No | Message not submitted error message not coming Error if no message entered Not working
|  |  |  | Add email log |  | Add Email log | Yes | Yes | No | Without Message not submitted error message not coming Error if no message entered Not Working
|  |  |  | Add sms log |  | Add SMS log | Yes | Yes | No | Without Message not submitted error message not coming Error if no message entered No Submit working
|  |  |  | Add listing |  | Sending listing to client | No | Yes | No | Not working Add + icon to add in bulkSend in one mail)
|  |  |  | Marketing |  | important links | No | No | No | NO active link or add link
|  |  |  | Collections |  | Add email to some collections | No | No | No | No action on Check box No area to Add
|  |  |  | Projects |  | View Project interested | No | No | NO
|  |  |  | Action - Delete | [5 empty] | Pop-up to verify delete
|  |  |  | Pagination | [5 empty] | Default to 20 with option to increase
|  | Engagement | Landing page | [9 empty] | Every column to have a diff bg color
|  |  |  | quick edit | [5 empty] | Not saving
view details
|  | Status View | [10 empty] | all columns shud be same display and colors as earlier pages
|  | Type view | [7 empty] | Not saving
|  | Group view | [7 empty] | Edit now working
|  | Stage view | [10 empty] | all columns shud be same display and colors as earlier pages
| Import leads | [8 empty] | Not working
Add leads
Save

## Lead Field List
Lead Action
Send Email Popup | Field | Data Type | Mandatory | Default | Allowed Values | Limit
| Subject | String | Y | string | text content | 100
| Body | String | Y | string | text content | 2000
Send SMS popup | Message | String | Y | string | text content | 140
Add Note | Message | String | Y | string | text content | 500
Add Call Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add Email Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add SMS Log | Message | String | N | string | text content | 140
| Log Type | String | Y | string | Radio Select
Qualification | Looking For City | String | Y | string | text content
Buyer Preferences | Currently Rent | String | Y | Empty | ??
| Down Payment | String | Y | Percentage | ??
| Payment Value | Number | Y | >0
| Price Range Start | Number | Y | >0
| Price Range End | Number | Y | > Price Range Start
| Buy Before Sell | Bool | N | FALSE
| Signed to sell | Bool | N | FALSE
| Preapproved Lender | Bool | N | FALSE
| Bed Room | Number | Y | >0
| Bath | Number | Y | >0
| Sq. Ft. | Number | N | >0
| Preffered Location | String | N
| Prop. Type | String | N
| Date | Date | N
| Desc | String | N
Seller Preferences | Reason | String | N
| Expected Price | Number | Y | >0
| By When | String | N
| Listed Property | Bool | N | FALSE
| Looking for New | Bool | N | FALSE
| Neighbour hood | String | N
| Desc | String | N
Investor Preferences | Location | String | Y
| Strategy | String | N
| Property Type | String | Y | Condo
| Price Range Start | Number | N | >0
| Price Range End | Number | N | > Rage Start
| How many deals | Number | N
| Expected Profit | Number | N
| Risk Capacity | String | N
| Notes | String | N
Edit Leads | Title | String | Y | Mr.
| First Name | String | Y | string |  | 100
| Last Name | String | N | string |  | 100
| Email | String | Y | string |  | 100
| Mobile | String | Y | string |  | 10 digit number
| Secondary Phone | String | Y | string |  | 10 digit number
| Ext | String | N | string |  | 3-6 digit number
| Type | String | Y | string |  | Database
| Status | String | Y | string |  | Database
| Group | String | N | string |  | Database
| Stage | String | N | string |  | Database
| Deal Value | Number | N | number | 0
| Win | String | N | string |  | Database
| Source | String | N | string |  | Database
| Reffered By | String | N | string
| Refferal Code | String | N | string
| Exp. Date | datetime | N | date
| Submitted Date | datetime | N | date
| Notes | String | N |  |  |  | 300
Appointment | Agenda | String | Y | string |  |  | 150
| Date | Datetime | Y | date |  |  | Futture Date
| Start Time | Time | Y | Time
| End time | Time | Y | Time |  |  | > Start Time
| Appointment Type | int | Y |  |  |  | DB
| AppointMent Priority | int | Y |  |  |  | DB
| Location Type | int | Y |  |  |  | DB
| Meeting Location Link | string | Y (Conditional)
Add Notes | Notes | String | Y | string |  |  | 500
Followup | Notes | String | Y | string |  |  | 500
| Folowup Date | Datetime | Y | date
Add Call Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add Email Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add SMS Log | Message | String | Y | string | text content | 140
Add Listing | MLS Id | String | Y | string | text content
| MLS Link | String | Y | string | text content
Add Marketing
Add To collections

## Contacts
Module | Page | Section | Sub-section | Item | Field List Ref | Element/Desc | API | Web/Design | Integration | Action | SMS Template required | Email Template Required | Design
Contacts
All Leads
|  | Grid view | Filters
|  |  |  | Search by name |  | Search on Frist Name, Last Name, Email, Phone | Yes | Yes | No
|  |  |  | Last contact |  |  | API changes done | No | No | To Be Removed
|  |  |  | Status |  | To be fetched from DB | Yes | Yes | No
|  |  |  | Delete |  | Delete Selected items | No | No | No
|  |  |  | Search button |  |  | Yes | Yes | No
Grid
|  |  |  | checkbox |  | Delete | No | No | No | To be included
|  |  |  | Quick Edit |  | Go to Edit button | Yes | No | No
|  |  |  | Send email |  | Send Email popup | No | No | No
|  |  |  | Send SMS |  | Send SMS popup | No | No | No
|  |  |  | Add note |  | Add Note popup | Yes | No | No
|  |  |  | add call log |  | Add Call log | Yes | No | No
|  |  |  | add email log |  | Add Email log | Yes | No | No
|  |  |  | add sms log |  | Add SMS log | Yes | No | No
|  |  |  | set next follow up |  | Add Next Followup | Yes | No | No
|  |  |  | Buyer Preferences |  | View | Yes | Yes | Yes
[6 empty] | Save | Yes | Yes | Partial | Buyer preferences not saving 3 checkbox questions
|  |  |  | Seller Preferences |  | View | No | Yes | No
[6 empty] | Save | No | No | No
|  |  |  | Investor Preferences |  | View | No | No | No | Form not completed
[6 empty] | Save | No | No | No
|  |  |  | Action - View Details |  | Basic Details | Yes | Yes | Yes | If save on any internal form, its not reloading the All Activity page For a second, its showing mohitgrover in email and it get updated to real contact Top Info box showing numeric information
|  |  |  | Edit Contact |  | Field Old values | Yes | Yes | No | How Often having wrong dropdown Is Vendor ?? Industry is missing if it requires for secondary contact | Add Industry in Main Contact
|  |  |  | Save Contact |  |  | Yes | Yes | No | Not Working
|  |  |  | Secondary Contact |  | Field Old Values | No | Yes | No | No save button
[7 empty] | No | No | No
|  |  |  | Important Dates |  | Field Old Values | No | Yes | No | No save button
[7 empty] | No | No | No
|  |  |  | Action View - All Activities |  | View Old All Activities | Yes | Yes | Yes | Loader is missing. Auto loading not exist
|  |  |  | View Appointments |  | Loading Appointments history | Yes | No | No | Not loading history data
|  |  |  | Save Appointment |  | Saving new appointment in DB | Yes | Yes | Yes | Saving but not re loading the history
|  |  |  | View Notes |  | Loading Note history | Yes | Yes | Yes
|  |  |  | Save Notes |  | Saving new Note in DB | Yes | Yes | Yes | Note is saving
|  |  |  | Add call log |  | Add Call log | Yes | Yes | Yes | Message not submitted error message not coming if type not selected
|  |  |  | Add email log |  | Add Email log | Yes | Yes | Yes | Message not submitted error message not coming if type not selected
|  |  |  | Add sms log |  | Add SMS log | No | No | No | We should have SMS also
|  |  |  | Refferals |  | Referrals list | No | No | No
|  |  |  | Transaction |  | Transaction of what | No | No | No
|  |  |  | Interested in |  | Interested projects | No | No | No | To be linked with client/lead
|  |  |  | Action - Delete | [5 empty] | Pop-up to verify delete
|  |  |  | Pagination | [5 empty] | Default to 20 with option to increase
|  | Classification View |  |  |  |  | No | No | No | Not available, Classification Property missing |  |  | Every column to have a diff bg color
|  | Contact Activites |  |  |  |  | No | No | No | Not Available |  |  | all columns shud be same display and colors as earlier pages
|  | Referral View |  |  |  |  | No | No | No | Not Available
|  | Review Management |  |  |  |  | No | No | No | Not Available
all columns shud be same display and colors as earlier pages
| Add Contact | [5 empty] | Yes | Yes | No | Is Investor, Marital status missing in Edit form

## Contact Field List
Ghanshyam
Contact Actions
Send Email Popup | Field | Data Type | Mandatory | Default | Allowed Values | Limit
| Subject | String | Y | string | text content | 100
| Body | String | Y | string | text content | 2000
Send SMS popup | Message | String | Y | string | text content | 500
Add Note | Message | String | Y | string | text content | 500
Add Call Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add Email Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add SMS Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Buyer Preferences | Currently Rent | String | Y | Empty | ??
| Down Payment | String | Y | Percentage | ??
| Payment Value | Number | Y | >0
| Price Range Start | Number | Y | >0
| Price Range End | Number | Y | > Price Range Start
| Buy Before Sell | Bool | N | FALSE
| Signed to sell | Bool | N | FALSE
| Preapproved Lender | Bool | N | FALSE
| Bed Room | Number | Y | >0
| Bath | Number | Y | >0
| Sq. Ft. | Number | N | >0
| Preffered Location | String | N
| Prop. Type | String | N
| Date | Date | N | Should be future
| Desc | String | N
Seller Preferences | Reason | String | N
| Expected Price | Number | Y | >0
| By When | String | N
| Listed Property | Bool | N | FALSE
| Looking for New | Bool | N | FALSE
| Neighbour hood | String | N
| Desc | String | N
Investor Preferences | Location | String | Y
| Strategy | String | N
| Property Type | String | Y | Condo
| Price Range Start | Number | N | >0
| Price Range End | Number | N | > Rage Start
| How many deals | Number | N
| Expected Profit | Number | N
| Risk Capacity | String | N
| Notes | String | N
Edit Contacts | Title | String | Y | Mr.
| First Name | String | Y | string |  | 100
| Last Name | String | N | string |  | 100
| Email | String | Y | string |  | 100
| Mobile | String | Y | string |  | 10 digit number
| Home Phone | String | N | string |  | 10 digit number
| Office Phone | String | N | string |  | 10 digit number
| Ext | String | N | string |  | 3-6 digit number
| Address Location | String | N | string
| Suite | String | N | string
| City | String | N | string
| Postal | String | N | string
| Province | String | N | string
| Country | String | N | string
| Last Contact Date | DateTime | N | date
| Company/Organizaiton | String | N | string
| Is Client | Bool | Y |  | FALSE
| Is Vendor | Bool | Y |  | FALSE
| Is Investor | Bool | Y |  | FALSE
| Maital Status | String | N | string
| Job Title | String | N | string
| Type | String | Y | string |  | Database
| Status | String | Y | string |  | Database
| How offen to connect | Number | N | string |  | 0 |  | 1m | 7d
Secondary Contact | Title | String | Y | Mr.
| First Name | String | Y | string |  | 100
| Last Name | String | N | string |  | 100
| Email | String | Y | string |  | 100
| Mobile | String | Y | string |  | 10 digit number
| Company/Organizaiton | String | N | string
| Job Title | String | N | string
| Office Phone | String | N | string |  | 10 digit number
| Ext | String | N | string |  | 3-6 digit number
| Industry | String | N | string
Important Dates | Type | String | Y | string
| Month | Number | Y | string |  | 1-12 only
| Day of Month | Number | Y | string |  | 1-31 only | Should be as per the month
Meeting | Agenda | String | Y | string |  |  | 150
| Date | Datetime | Y | date |  |  | Futture Date
| Start Time | Time | Y | Time
| End time | Time | Y | Time |  |  | > Start Time
| Appointment Type | int | Y |  |  |  | DB
| AppointMent Priority | int | Y |  |  |  | DB
| Location Type | int | Y |  |  |  | DB
| Meeting Location Link | string | Y (Conditional)
Add Notes | Notes | String | Y | string |  |  | 500
Add Call Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add Email Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add SMS Log | Message | String | Y | string | text content | 140

## Client
Module | Page | Section | Sub-section | Item | Field List Ref | Element/Desc | API | Web/Design | Integration | Action | SMS Template required | Email Template Required | Design
Clients |  |  | Dshboard | Active client |  | Count of clients (active) | No | Yes | No
[6 empty] | Forecast Revenue | No | Yes | No
| All Clients |  |  |  |  | Monthly Goal | No | Yes | No
|  |  |  | Upcoming Activities |  | View List | No | No | No
[6 empty] | View Appointment details | No | No | No
[6 empty] | View Showing Details | No | No | No
[6 empty] | View Openhouse | No | No | No
[6 empty] | View Seller Showings | No | No | No
|  |  |  | Client interactions/Notifications |  | View List | No | No | No
[6 empty] | View Document | No | No | No
[6 empty] | View Messages | No | No | No
|  |  | Add Client | Add new client |  | Form to add client | Yes | No | No | 1) Missing Type from DB 2) Missing Source from DB 3) Missing Title 4) Mobile validation missing 5) phone validation missing 6) Email Validation missing 7) Google API in Address missing 8) Office phone validation missing Ext missing
|  | Grid view | Filters
|  |  |  | Search by name |  | Search on Frist Name, Last Name, Email, Phone | No | No | No
|  |  |  | Status |  | To be fetched from DB | No | No | No
|  |  |  | Delete |  | Delete Selected items | No | No | No
|  |  |  | Search button |  |  | No | No | No
|  |  | Grid | [6 empty] | Email, Phone and Status missing
|  |  |  | checkbox |  | Delete | No | No | No | To be included
|  |  |  | Quick Edit |  | Go to Edit button | No | No | No | Good to have
|  |  |  | Send email |  | Send Email popup | No | No | No | Good to have
|  |  |  | Send SMS |  | Send SMS popup | No | No | No | Good to have
|  |  | Client Dashboard | Landing Page |  | Basic Details Info | No | No | No
|  |  |  | Mortgage Contact |  | Grid | No | No | No
|  |  |  | Legal Contacts |  | Grid | No | No | No
|  |  |  | Upcoming Activities |  | Grid | No | No | No
|  |  | Profile | Edit Page |  | Edit Form | Yes | Yes | No | 1) Missing Type from DB 2) Missing Source from DB 3) Missing Title 4) Mobile validation missing 5) phone validation missing 6) Email Validation missing 7) Google API in Address missing 8) Office phone validation missing Ext missing 10) Secondary Title DB missing 11) Mobile validation missing 12) phone validation missing 13) Email Validation missing 14) Google API in Address missing 15) Office phone validation missing Save not working
|  |  |  | Important Dates |  | Submit | Yes | Yes | Yes
[6 empty] | View List | Yes | Yes | Yes
[6 empty] | Delete | Yes | Yes | Yes
|  |  |  | Add Child |  | Add New | Yes | Yes | Yes
[6 empty] | View List | Yes | Yes | Yes
[6 empty] | Delete | Yes | Yes | Yes
|  |  |  | Add note |  | Add Note popup | Yes | No | No
|  |  |  | add call log |  | Add Call log | Yes | No | No
|  |  |  | add email log |  | Add Email log | Yes | No | No
|  |  |  | add sms log |  | Add SMS log | Yes | No | No
|  |  |  | set next follow up |  | Add Next Followup | Yes | No | No
|  |  |  | Buyer Preferences |  | View | Yes | Yes | Yes
[6 empty] | Save | Yes | Yes | Partial | Buyer preferences not saving 3 checkbox questions
|  |  |  | Seller Preferences |  | View | No | Yes | No
[6 empty] | Save | No | No | No
|  |  |  | Investor Preferences |  | View | No | No | No | Form not completed
[6 empty] | Save | No | No | No
|  |  |  | Action - View Details |  | Basic Details | Yes | Yes | Yes | If save on any internal form, its not reloading the All Activity page For a second, its showing mohitgrover in email and it get updated to real contact Top Info box showing numeric information
|  |  |  | Edit Contact |  | Field Old values | Yes | Yes | No | How Often having wrong dropdown Is Vendor ?? Industry is missing if it requires for secondary contact | Add Industry in Main Contact
|  |  |  | Save Contact |  |  | Yes | Yes | No | Not Working
|  |  |  | Secondary Contact |  | Field Old Values | No | Yes | No | No save button
[7 empty] | No | No | No
|  |  |  | Important Dates |  | Field Old Values | No | Yes | No | No save button
[7 empty] | No | No | No
|  |  |  | Action View - All Activities |  | View Old All Activities | Yes | Yes | Yes | Loader is missing. Auto loading not exist
|  |  |  | View Appointments |  | Loading Appointments history | Yes | No | No | Not loading history data
|  |  |  | Save Appointment |  | Saving new appointment in DB | Yes | Yes | Yes | Saving but not re loading the history
|  |  |  | View Notes |  | Loading Note history | Yes | Yes | Yes
|  |  |  | Save Notes |  | Saving new Note in DB | Yes | Yes | Yes | Note is saving
|  |  |  | Add call log |  | Add Call log | Yes | Yes | Yes | Message not submitted error message not coming if type not selected
|  |  |  | Add email log |  | Add Email log | Yes | Yes | Yes | Message not submitted error message not coming if type not selected
|  |  |  | Add sms log |  | Add SMS log | No | No | No | We should have SMS also
|  |  |  | Refferals |  | Referrals list | No | No | No
|  |  |  | Transaction |  | Transaction of what | No | No | No
|  |  |  | Interested in |  | Interested projects | No | No | No | To be linked with client/lead
|  |  |  | Action - Delete | [5 empty] | Pop-up to verify delete
|  |  |  | Pagination | [5 empty] | Default to 20 with option to increase
|  | Classification View |  |  |  |  | No | No | No | Not available, Classification Property missing |  |  | Every column to have a diff bg color
|  | Contact Activites |  |  |  |  | No | No | No | Not Available |  |  | all columns shud be same display and colors as earlier pages
|  | Referral View |  |  |  |  | No | No | No | Not Available
|  | Review Management |  |  |  |  | No | No | No | Not Available
all columns shud be same display and colors as earlier pages
| Add Contact | [5 empty] | Yes | Yes | No | Is Investor, Marital status missing in Edit form

## Client Field List
Client Action
| Title | String | Y | Mr.
| First Name | String | Y | string |  | 100
| Last Name | String | N | string |  | 100
| Email | String | Y | string |  | 100
| Mobile | String | Y | string |  | 10 digit number
| Home Phone | String | N | string |  | 10 digit number
| Office Phone | String | N | string |  | 10 digit number
| Ext | String | N | string |  | 3-6 digit number
| Address Location | String | N | string
| Suite | String | N | string |  |  | Internal from Google API
| City | String | N | string |  |  | Internal from Google API
| Postal | String | N | string |  |  | Internal from Google API
| Province | String | N | string |  |  | Internal from Google API
| Country | String | N | string |  |  | Internal from Google API
| Job Title | String | N | string
| Company/Organizaiton | String | N | string
| Industry | String | N | string
| Notes/Comments | String | Y | string | text content | 2000
Send SMS popup | Message | String | Y | string | text content | 500
Add Note | Message | String | Y | string | text content | 500
Add Call Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add Email Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add SMS Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Buyer Preferences | Currently Rent | String | Y | Empty | ??
| Down Payment | String | Y | Percentage | ??
| Payment Value | Number | Y | >0
| Price Range Start | Number | Y | >0
| Price Range End | Number | Y | > Price Range Start
| Buy Before Sell | Bool | N | FALSE
| Signed to sell | Bool | N | FALSE
| Preapproved Lender | Bool | N | FALSE
| Bed Room | Number | Y | >0
| Bath | Number | Y | >0
| Sq. Ft. | Number | N | >0
| Preffered Location | String | N
| Prop. Type | String | N
| Date | Date | N | Should be future
| Desc | String | N
Seller Preferences | Reason | String | N
| Expected Price | Number | Y | >0
| By When | String | N
| Listed Property | Bool | N | FALSE
| Looking for New | Bool | N | FALSE
| Neighbour hood | String | N
| Desc | String | N
Investor Preferences | Location | String | Y
| Strategy | String | N
| Property Type | String | Y | Condo
| Price Range Start | Number | N | >0
| Price Range End | Number | N | > Rage Start
| How many deals | Number | N
| Expected Profit | Number | N
| Risk Capacity | String | N
| Notes | String | N
Edit Contacts | Title | String | Y | Mr.
| First Name | String | Y | string |  | 100
| Last Name | String | N | string |  | 100
| Email | String | Y | string |  | 100
| Mobile | String | Y | string |  | 10 digit number
| Home Phone | String | N | string |  | 10 digit number
| Office Phone | String | N | string |  | 10 digit number
| Ext | String | N | string |  | 3-6 digit number
| Address Location | String | N | string
| Suite | String | N | string
| City | String | N | string
| Postal | String | N | string
| Province | String | N | string
| Country | String | N | string
| Last Contact Date | DateTime | N | date
| Company/Organizaiton | String | N | string
| Is Client | Bool | Y |  | FALSE
| Is Vendor | Bool | Y |  | FALSE
| Is Investor | Bool | Y |  | FALSE
| Maital Status | String | N | string
| Job Title | String | N | string
| Type | String | Y | string |  | Database
| Status | String | Y | string |  | Database
| How offen to connect | Number | N | string |  | 0 |  | 1m | 7d
Secondary Contact | Title | String | Y | Mr.
| First Name | String | Y | string |  | 100
| Last Name | String | N | string |  | 100
| Email | String | Y | string |  | 100
| Mobile | String | Y | string |  | 10 digit number
| Company/Organizaiton | String | N | string
| Job Title | String | N | string
| Office Phone | String | N | string |  | 10 digit number
| Ext | String | N | string |  | 3-6 digit number
| Industry | String | N | string
Important Dates | Type | String | Y | string
| Month | Number | Y | string |  | 1-12 only
| Day of Month | Number | Y | string |  | 1-31 only | Should be as per the month
Meeting | Agenda | String | Y | string |  |  | 150
| Date | Datetime | Y | date |  |  | Futture Date
| Start Time | Time | Y | Time
| End time | Time | Y | Time |  |  | > Start Time
| Appointment Type | int | Y |  |  |  | DB
| AppointMent Priority | int | Y |  |  |  | DB
| Location Type | int | Y |  |  |  | DB
| Meeting Location Link | string | Y (Conditional)
Add Notes | Notes | String | Y | string |  |  | 500
Add Call Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add Email Log | Message | String | N | string | text content | 500
| Log Type | String | Y | string | Radio Select
Add SMS Log | Message | String | Y | string | text content | 140